## Project Timeline
Project Timeline
Line chart that plots each milestone on the corresponding timeframe is in this cell.
Project Milestones
Date (MM/DD/YYYY) | Activities | Assigned To | Milestones | Baseline | Project Timeline Tip
2022-10-24 | Project Start | S.R. VIDHYAMBIKA | 0 | 0 | Use the Position field in the Project Milestones table to place the milestone labels where you want! Use positive numbers to position them above the timeline and negative numbers to position them below.
2022-11-04 | Find best performed ML algm | S.R. VIDHYAMBIKA | 1 | 0
2022-11-06 | Deploy & code Sprint 1 | S.R. VIDHYAMBIKA | 2 | 0
2022-11-09 | Complete Sprint 2 | S.R. VIDHYAMBIKA | 3 | 0
2022-11-12 | Complete Sprint 3 | S.R. VIDHYAMBIKA | 4 | 0
2022-11-15 | Test software & rectify errors | S.R. VIDHYAMBIKA | 5 | 0
2022-11-19 | Complete Sprint 4 | S.R. VIDHYAMBIKA | 6 | 0
2022-11-19 | Project End | S.R. VIDHYAMBIKA | 7 | 0